## How to use
Daily Manpower Report (Construction): how to use this template
1 | Fill one 'Daily Report' sheet per site per day. Copy the sheet for each new day.
2 | Complete the header: project, site, date, weather and who prepared the report.
3 | For each trade and contractor, enter the planned and present headcount. Absent and totals calculate automatically.
4 | Record total hours, overtime hours and the activity or location where each gang worked (e.g. Block B slab, 4th floor plastering).
5 | List your own staff (engineers, supervisors, safety) separately at the bottom of the table.
6 | Copy each day's 'Present' totals into the 'Monthly Labour-Days' sheet to build the contractor-wise total used to check labour bills.
Tip: this sheet is only as accurate as the attendance typed into it. Bazat Tracker fills the same numbers automatically from face-verified, geofenced punches at each site, and runs payroll from them. bazattracker.com

## Daily Report
Daily Manpower Report
Construction site daily labour and staff record. Sample entries are illustrative; overwrite them.
Project |  |  |  | Site / Location
Date |  |  |  | Weather | Clear / Rain / Hot
Prepared By |  |  |  | Verified By
S.No | Trade / Category | Contractor | Planned | Present | Absent | Total Hours | OT Hours | Activity / Work Location | Remarks
1 | Mason | Contractor A | 12 | 11 |  | 88 | 0 | Block B, 4th floor brickwork
2 | Helper / Mazdoor | Contractor A | 18 | 16 |  | 128 | 8 | Block B, material shifting
3 | Carpenter (Shuttering) | Contractor B | 8 | 8 |  | 64 | 16 | Block C slab shuttering (night pour)
4 | Bar Bender
5 | Electrician
6 | Plumber
7 | Painter
8 | Welder / Fabricator
9 | Tile Layer
10 | Other
11 | Site Engineer | Own staff
12 | Supervisor / Foreman | Own staff
13 | Safety Officer | Own staff
14 | Store Keeper | Own staff
Total Manpower
Key Work Done Today |  |  |  |  | Issues / Delays
Site Engineer (Sign) |  |  |  |  | Project Manager (Sign)

## Monthly Labour-Days
Monthly Labour-Days by Contractor
Enter each day's 'Present' count per contractor and trade. Compare the total with the contractor's bill.
Project / Site |  |  |  | Month
Contractor | Trade | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Total Labour-Days
Contractor A | Mason
Contractor A | Helper / Mazdoor
Contractor B | Carpenter (Shuttering)
Total